## EXPENSE REPORT
Sustainability Committee Project Tracker
Purpose | Reduce, Recycle, Reuse, Biodegradable |  |  | Strategy | Change Item, Remove Item, Change Practice, New Practice
Item | Project | Category | Strategy | Status | Cost | Savings in Money | Savings in Waste | Project Lead | Environmental Impact | Challenges | Mitigation for Challenges | Notes Including any Safety and Quality impact
| 1. Paper Pill Cup Project | Biodegradable | Change Item | Complete | 1.3c/cup (paper) vs 9.3c/cup (plastic) | 485 cups/year = $630.50 vs $4510.50 ($3880 saving) | 26kg of plastic in 6 months. Estimated 52kg/year or more. | Sharon |  |  |  | Implemented December 2022 with no barriers to success currently
| 2. Reusable NIBP Cuff | Reusable | Change Item | Unable to proceed - Not supported by IPAC |  |  |  | David |  | Cleaning of reusables | Use wipes for cleaning locally | Not supportted by xxxx - 17 March
| 3. Reusable Finger Probe | Reusable | Change Item | Able to Proceed! Supported by IPAC 19th May 2023 | $13.55/probe vs $0/probe (already owned) | 10282 probes/year = <$139,326.26 saved | 7.06kg plastic in 2 months. Esimated 42.36kg/year or more. | Emma | TBD | Cleaning of reusables | Use wipes for cleaning locally | Not supported by xxxx - 17 March. Supported by xxxx 19th May. More probes procured in June. Policy commenced for all setups in July.
| 4. Linen-Washed Slide Sheets | Reusable | Change Item | Able to Proceed! Supported by IPAC 19th May 2023 | $5.17/sheet (single) vs 0.41c/sheet (re-use) | 3349 sheets/year = $17,320.26 vs $1373.09 ($15947.17 saving) | 26.25kg plastic per month so far. Estimated 315kg/year or more. | Bruce | TBD |  |  | Trial in xx ward started week of 29th May following nurse education. Full ICS rollout commenced succesfully July.
| 5. PVC Recycling Bins | Recycling | New Practice | Waiting for bin procurement, aiming to commence early 2023. | David | [6 empty] | Internal bin procurement and placement required, Baxter will provide education on the project following this.
| 6. Recycling Bins | Recycling | New Practice | Waiting for IPAC | Robin | [6 empty] | xxx Health ready. Awaiting xxxx approval to roll out. Unsure of space for bins
| 7. Biodegradable Masks | Biodegradable | Change Item | Unable to proceed - Not supported by IPAC | [7 empty] | xxxx to contact Clinical Products for information Discussed with IPAC who stated they will not support recycling of clinical waste. Being discussed at district level. No further ICU action.
| 8. Calculating ICU Waste Production | Reduce | Change Practice | DR Investigation shows ICU waste is not measured unfortunately. | [7 empty] | xx to contacted xxxx waste for possible data in March 2023. Unfortunately unit-specific waste data is not measured by the hospital.
| 9. Stopping using plastic bags for ICU setups | Reduce | Change Practice | Done in E3B | [7 empty] | Currently rolled out to all of general ICU.
| 10. Glass bottle waste management | Recycle | Change Practice | Awaiting specifics from Domestic Services | [7 empty] | Glass bin on wheels available from domestic services; nurses put in dirty utility. Sharpsmart bins. Need a trial in E3C. Terrie Black helping to organise
| 11. ABG reduction in the ICU with a flowchart/algorithm for ABGs (trailed successfully in Adelaide) | Reduce | Change Practice | Under discussion | [7 empty] | Collaboration with xxxx, Adelaide CNE, xxx, xxx and ANZICS. Ali to contact POCT for baseline ABG cost/usage data. Need form to fill for nurses for each ABG for "why?"
| 12. Co-mingled recycling in Tea Rooms (yellow bin) - 8 bins for the 4 pods | Recycling | New Practice | Under Discussion | [7 empty] | xxx, xxx discussing with NUMs and environmental etc on viability
| 13. Sustainability Projects evaluation survey |  | MS Forms online survey | Completed | nil | [6 empty] | ICU sustainability projects one page summary developed and distriubuted in response to feedback.
| 14. Plastic bags on suction tubing can be re-used? | recycle | New Practice | [8 empty] | xxxxx investigating
| 15. Reducing HAPI/Bluey use per patient | reduce | Change practice | Project approved, phase one survey audit of current use commencing week starting November 6 2023. | nil | 17880 of XL pad used per year on avg in ICU at $44506.30 spent | 17880 x weight of 190x90cm pad |  |  |  |  | xxx and xxx from zone C leading this project.
| 16. Surgical Steel recycling Project | Reuse | Change item | under investigation | re-usable item cost. CSSD reprocessing cost | 7698 items used per year on avg in ICU at $16397.92 spent | 7698 x 0.037kg avg weight = 284.826kg metal per year |  |  |  |  | District sustainability committee investigating with CSSD. Usage data provided by xxx. Meeting Thurs 10th Aug.
| 17. Neuro Torch cleaning project | reuse | Change Practice | commenced 09/08 | nil | 2643 items used per year on avg in ICU @$1612.13 spent | 66.075kg metal and batteries per year |  |  |  |  | xxxx says yes. respiratory staff to clean. Educate and advertise to not throw pen torches away. posters.
Absolute Total | [5 empty] | 221669.78 | 409.36kg plastic/year 350.901kg metal/year
Net Total | [5 empty] | TBC after 1 year | TBC after 1 year
APPROVED |  |  |  |  | NOTES